## Client Response
# | Client Observation | Root Cause | Current Status / Action Taken | Plan of Action | Priority
1 | BBX2/BBX3 vessel capacity looks inconsistent - BBX2's 735 TEU reserved-for-slotters figure isn't reflected, and BBX3's effective capacity doesn't reconcile the same way | Capacity is currently calculated using one flat number per vessel type (rank), not factoring in each line's individually reserved/slotted capacity from the proforma data - so BBX2 and BBX3 are both computed the same simplified way | Root cause identified and confirmed against the source data. Fix being implemented. | Wire each line's actual reserved-capacity figure into the capacity calculation so it reflects real, per-line numbers instead of one generic figure per vessel type | High
2 | BMX rotation duration (25.77 days) isn't a multiple of 7 | Same root cause as #3 - the underlying duration constraint is always an exact multiple of 7; the figure seen came from manually summing per-port timing values affected by the issue in #3 | Investigated and confirmed this is not an independent issue - tracked together with #3. | Resolved once #3 is fixed | High (bundled with #3)
3 | BMX wait/manoeuvring times show as 0 after JPYOK was added, though proforma shows 197 hours | When a port is added to a line, per-port operational detail (wait/manoeuvring time) isn't currently recalculated for the new line shape, so it defaults to zero | Root cause identified and confirmed reproducible for this exact scenario (port added to a line). Fix being tested | Fix the underlying data linkage so operational timing is correctly recalculated whenever a line's port sequence changes | High
4 | VSA (partner) service schedules appear to be changing even though those lines should be frozen | Topology, weekly schedule, and vessel type are correctly locked for VSA lines. Sailing speed is intentionally left flexible (locking it caused solver infeasibility against the partner's own schedule data). Port stay times, however, are not yet locked the same way - likely source of the drift observed | Confirmed topology/schedule/vessel type locking is working as intended. Identified the stay-time gap as the likely cause. Fix being tested | Lock port stay times for VSA lines, consistent with how topology/schedule/vessel type are already locked | High
5 | BBX is sailing at a constant 19kts, appearing to exceed the 16.5kt soft-cap speed rule | The 16.5kt soft-cap penalty does exist in the model, but there is a calibration error in how it's applied - it currently starts discouraging speed too early (13.5kt) rather than at the intended 16.5kt threshold. Why BBX specifically still reaches the 19.0kt ceiling despite the fuel penalty is still under investigation | Calibration bug identified and fix designed, not yet implemented. Separately, investigation ongoing into why BBX reaches the top of the allowed range. | (a) Fix the miscalibrated penalty so it applies at the correct 16.5kt threshold; (b) continue investigating why BBX rides the top of the allowed range | Medium
6 | Ports with no cargo movement (CNCWN, MYLBU) are being added to services with no apparent benefit | The model currently doesn't check whether a candidate port addition will actually move any cargo before accepting it into a route - it only checks that the route shape itself is valid | Root cause identified. Fix requires a change inside the core route-search logic (larger than the other items), so it is being scoped as its own piece of work. Yet to implement | Add a check so the model rejects a port addition if it results in zero cargo movement | Medium
7 | Cargo flow routing isn't visible in the output, making it hard to fully review output quality | The underlying routing is already calculated internally - it's just not currently included in the exported output file | Confirmed the data already exists internally. Export addition implemented, yet to test | Add cargo flow routing (by OD pair/path) to the exported output | Medium
8 | Clarification requested on "vrank_mix", and the difference between "capacity" and "weekly_capacity_teu" | vrank_mix shows the mix of vessel types on a line when more than one type is used (e.g. "5:2;6:1" = 2 ships of type 5, 1 of type 6). Separately, capacity and weekly_capacity_teu were incorrectly showing identical values due to an export bug | Complete. vrank_mix clarified (no change needed). capacity/weekly_capacity_teu duplicate-column bug fixed and verified. | vrank_mix: no change needed, documented for clarity. capacity/weekly_capacity_teu: fixed - capacity now correctly shows total fleet capacity, distinct from the per-week figure | Done